## Slide 1
Project Charter: Team 4-RMS Titanic
Case for change / Problem Statement
UConn MS BAPM students are not equipped to recognize systematic biases and have limited experience managing projects which is likely to lead to future project failures and inefficiencies.
Objectives / Goal statements
Deliver a presentation that shows we understand and can recognize systematic biases and other project management techniques. Prepare ourselves for future projects by utilizing best practices, project management tools and techniques as well as familiarizing ourselves with systematic biases in order to recognize them in the future.
In Scope | Out of Scope
Deliver an in class PowerPoint presentation. | Writing a Paper on the Project Topic.
Researching on the topic and identifying potential systematic biases and points of failure | Interviewing research project participants.
Provide documentation for other project deliverables such as Gantt Chart, WBS and Project Charter. | Analyze and comparing other project topics.
Constraint Matrix |  |  | 
 | MOST | SOME | LEAST
SCOPE |  | X | 
TIME | X |  | 
COST |  |  | X
Top Risks (max. 5)
Unavailability/Absence of team members during project meetings and final presentation. Conflicts within the project team. Not meeting project deadlines. Encounter technical difficulties like Software issues and Projection errors while delivering the final presentation.
Business Case
The team needs to gain experience by mimicking a real world project case study allowing them to recognize and respond to systematic biases in order to minimize failing projects and successfully manage future projects.
Assumptions
Our project team has a basic understanding of systematic biases. Our project sponsor will guide us through this project, prepare feedback, and provide us with additional inputs as and when necessary. There will be sufficient information available to research our topic. The project topic will remain constant and not be changed.

## Slide 2: Project Charter: Team 4-RMS Titanic
Incoming Dependency | Outgoing Dependency
Project Topic | N/A
Project Rubrics and templates for final presentation. | N/A
Learning about topics in class to incorporate into project deliverables. | N/A
Deliverables & Milestones (High Level Milestone Plan) |  |  | 
Project Start Date: 9/15/2016 |  | Project End Date: 12/8/2016 | 
Key Deliverable | Milestone Name (MN) |  | Planned MS Date
Communication Plan |  |  | 9/22/2016
Project Charter |  |  | 9/29/2016
Revised Project Charter |  |  | 10/6/2016
Gantt Chart |  |  | 10/13/2016
Work Breakdown Structure |  |  | 10/13/2016
Project Updates 1 - 4 |  |  | Weekly 10/20/2016 – 11/10/2016
Presentation Slides |  |  | 11/27/2016
Formal In-Class Presentation |  |  | 12/8/2016
Signoff |  | 
Role | Signature | Date
Sponsor |  | 
PSB Member |  | 
Beneficiary |  | 
Beneficiary |  | 
Project Organization | 
Sponsor | Mark Tschiegg
PSB Members | Mark Tschiegg
Project Manager | Rotating between the Team Members.
Workstream Leaders | N/A
Team Members | Amy, Sri, Ram, Rik, Ted (Team 4)