## Slide 1: Project Update: Team 4/ RMS Titanic
Sponsor: Mark Tschiegg
Project Manager: Rikdev Bhattacharya
Data as of: 10/20/2016
All group members completed individual initial research on the RMS Titanic.
We have had an initial round of discussion in regard to the project failures and systematic biases.
We are waiting on confirmation regarding the scope from our project sponsor before we finalize systematic biases and complete further research.
Project Status
We have completed the Communication Plan, The Project Charter, The Gantt Chart, and The Work Breakdown Structure.
We have completed initial research and gathering of materials.
As a group, we have identified a number of potential systematic biases.
Key Achievements this period
Key Performance Indicators |  |  | 
Indicator | R | C | O
Overall |  | A | 
Scope |  | A | 
Schedule |  | G | 
Risks |  | R | 
Dependencies |  | A | 
Top Risks and Issues |  |  |  | 
R/I | Risk | P | I | Response Action
R | Do not receive clarification from project sponsor | L | H | Follow up with project sponsor via email or in class if necessary
R | Team member schedule conflicts | M | M | Reschedule meetings based on availability
R | Lack of agreement on systematic biases | L | H | Take a vote and follow up with project sponsor to confirm
I | Reallocation of Resources within Team | H | H | Welcome new team member and brief him about team achievements and planned activities; Reallocate planned activities assigned to Amy between the team members
I | Conflict with Group Document Sharing platform in Google Drive | M | M | New Google Drive Account to be created and old data from Amy’s account to be migrated
We will finalize the systematic bias or biases (no more than 2) that had the biggest impact on the failure of the Titanic.
We are going to identify the major tasks of the project and assigning resources.
Planned for next period
Should we include project issues and problems that are not directly related to the systematic biases that we identify?
Should we focus on the construction of the RMS Titanic or the maiden voyage or both?
Should we factor in conspiracy theories?
How should we incorporate the simultaneous construction and voyages of the RMS Olympic?
Questions for Sponsor