## Slide 1: Project Update: Team 4 / RMS Titanic
Sponsor: Mark Tschiegg
Project Manager: Chen-Wei Huang (Ted)
Data as of: 10/27/2016
Clarification received from Project Sponsor with regards to the queries on the scope; better clarity on project scope.
New team member welcomed in the team. A brief induction is given about the team’s past achievements and the current status.
We have had multiple rounds of discussions within the team and have shared the individual research material with the rest of the team.
We have finalized on two systematic biases that had the biggest impact on the failure of RMS Titanic.
The two systematic biases identified are ‘Groupthink’ and ‘Overconfidence’.
Project Status
Individual research material shared among the team.
Migrated all old data and research files to the new Google Drive that was created after Amy’s exit.
Induction of new team member.
Key Achievements this period
Key Performance Indicators |  |  | 
Indicator | R | C | O
Overall | A | G | 
Scope | A | G | 
Schedule | G | G | 
Risks | R | A | 
Dependencies | A | G | 
Top Risks and Issues |  |  |  | 
R/I | Risk | P | I | Response Action
R | Inability of the new team member to adapt to the change in project. | L | H | Assign a Project buddy for the new team member to adapt to the new project.
R | Team member schedule conflicts due to upcoming holiday weekend. | M | L | Reschedule meetings based on availability .
R | Inclement weather might impact the project deliverables and planned schedule. | M | L | Plan for Online/Webex sessions to meet and discuss instead of in-person meetings.
R | Conflicts arising out of change in team structure and dynamics. | M | M | Work on team building activities and refer to the communication plan for any escalations.
Study further about the two identified systematic biases and their impact on how they led to the failure of RMS Titanic.
Study Final Presentation rubric and allocate topic-wise deliverables/research to each team member, for in-depth research.
Planned for next period
Do we need to study and reference other projects which failed because of ‘Groupthink’ or ‘Overconfidence’ systematic bias?
Questions for Sponsor