## Slide 1: Project Update: Team 4 / RMS Titanic
Sponsor: Mark Tschiegg
Project Manager: Sriraman Srinivasan
Data as of: 11/3/2016
Team in high spirits with the return of Amy; Naren exited the team amicably.
Team communication norms and document sharing platforms reinstated.
Quick walkthrough given to Amy about project updates and plans that were made during her absence.
We shared experiences that we learnt from reallocated members and plan to incorporate best practices to improve team dynamics.
We reviewed the Final Presentation rubric and allocated topic-wise deliverables/research to each team member, for in-depth research.
Planned activity to study further about the two identified systematic biases delayed due to schedule conflicts; planned for next week.
Project Status
Assigning/Allocating topic wise deliverables to each team member.
Key Achievements this period
Key Performance Indicators |  |  | 
Indicator | R | C | O
Overall | G | A | 
Scope | G | G | 
Schedule | G | R | 
Risks | A | A | 
Dependencies | G | G | 
Top Risks and Issues |  |  |  | 
R/I | Risk | P | I | Response Action
R | Risk of not meeting deadlines. | M | H | Plan on frequent meetings to make sure the team is on track and support any struggling team members
R | Team member schedule conflicts due to resource engagements in other projects. | M | M | Reschedule meetings based on availability .
R | Inclement weather might impact the project deliverables and planned schedule. | M | L | Plan for Online/Webex sessions to meet and discuss instead of in-person meetings.
Study further about the two identified systematic biases and their impact on how they led to the failure of RMS Titanic.
Team to research on individual topic-wise deliverables assigned to each
Planned for next period
Can we make minor updates to the presentation slides after submission ( Between 27th Nov and Dec 8th) ?
Can we make an appointment with you for a discussion on the two selected systematic biases for our project ?
Questions for Sponsor