## Slide 1: Project Update: Team 4 / RMS Titanic
Sponsor: Mark Tschiegg
Project Manager: Sriram Rajagopalan
Data as of: 11/17/2016
Team members successfully researched the individual topics assigned to them.
We met with the project sponsor and understood more about the project priorities.
We discussed the content, theme, style and team member roles for our final deliverable.
With the extended deadlines, we covered significant ground and are back on schedule.
Project Status
Narrowed down to a single systematic bias and identified 4 key examples of Overconfidence bias in the project.
Defined team member roles and made template for Final presentation.
Team Celebration party at ‘City Steam’ on 10th Nov 2016 as scheduled.
Key Achievements this period
Key Performance Indicators |  |  | 
Indicator | R | C | O
Overall | A | G | 
Scope | G | G | 
Schedule | R | G | 
Risks | A | G | 
Dependencies | G | G | 
Top Risks and Issues |  |  |  | 
R/I | Risk | P | I | Response Action
R | Poor presentation preparation. | L | H | Do multiple virtual rehearsals as well as final in person rehearsal.
R | Team member unavailability/illness on the day of the final presentation. | L | H | Appropriate notes on everyone’s tasks and presentation roles.
R | Inclement weather might impact the project deliverables and planned schedule. | L | L | Plan for Online/Webex sessions.
R | Schedule and time conflicts during the Thanksgiving break. | L | L | Discuss each other’s availability and decide on meeting times and internal deadlines.
Build content that has to go into the presentation template.
Individual presentation practice.
Team presentation rehearsal.
Actual presentation on December 8th 2016.
Planned for next period
Questions for Sponsor